## Sheet1
Week 1
Product Owner | SCRUM Master | SCRUM Team
Kaushal | Arpit | Arpit Kumar
Kaushal Kumar
Rohan Chavan
Sharayu Milind Nalawade
Venkat Chakkani

## Product Backlog
USER STORY ID | USER STORY | Description | Priority | Complexity | Status
US001 | As a user, I want to be able to create a new account. | Implement account creation functionality | Critical | Medium | In Progress
US002 | As a user, I want to log in securely using my email and password. | Develop a secure authentication system for user logins and password management. | High | High | In Progress
US003 | As a user, I want to reset my password in case I forget it. | Add functionality for password reset via email. | Medium | Medium | In Progress
US004 | As a borrower, I want to upload required documents for loan processing (ID proof, income statements, etc.). | Implement functionality to update account information | low | low | In Progress
US005 | As a user, I want to view my account details | Implement deposit transaction functionality | Medium | Medium | In Progress
US006 | As a user, I want to deposit money into my account | Implement deposit transaction functionality | High | High | In Progress
US007 | As a user, I want to withdraw money from my account | Implement withdrawal transaction functionality | High | Medium | In Progress
US008 | As a user, I want to view my transaction history | Implement functionality to view transaction history | Medium | low | In Progress
US009 | As a user, I want to transfer funds between my accounts | Implement fund transfer functionality | Critical | High | In Progress
US010 | As a user, I want to view my recent transactions quickly | Implement caching for recent transactions | Medium | Medium | In Progress
US011 | As a user, I want to receive notifications for transactions | Implement transaction notification functionality | Medium | Medium | In Progress
US012 | As a user, I want to generate monthly reports of my account activities | Implement report generation functionality | Critical | Medium | In Progress
US013 | As an admin, I want to view various reports on user accounts and transactions | Implement admin reporting dashboard | Critical | Medium | In Progress
US014 | As a user, I want a responsive and user-friendly interface | As a user, I want a responsive and user-friendly interface | High | Medium | In Progress
US015 | As a user, I want my data to be secure | Implement security best practices across all services | Medium | High | In Progress
US016 | As a developer, I want to deploy services on AWS using Kubernetes | Set up Kubernetes clusters on AWS EKS and deploy services | High | High | In Progress
US017 | As a developer, I want to use managed databases for persistent storage | Configure and integrate AWS RDS for MySQL and MongoDB | Medium | High | In Progress
US018 | As a developer, I want to store static files and backups securely | Configure AWS S3 for static file and backup storage | Medium | low | In Progress
US019 | As a user, I want to reset my password if I forget it | Implement password reset functionality | Medium | High | In Progress
US020 | As a user, I want to be logged out after a period of inactivity | Implement session management and auto logout | Medium | low | In Progress
US021 | As a user, I want to receive email confirmations for significant account activities | Implement email notification system | Medium | Medium | In Progress
US022 | As a user, I want to have multi-factor authentication for added security | Implement multi-factor authentication | Medium | Medium | In Progress
US023 | As a user, I want to search for specific transactions in my transaction history | Implement search functionality in transaction history | low | low | In Progress
US024 | As an admin, I want to monitor the system's health and performance | Implement monitoring and logging for all services | Medium | Medium | In Progress

## Sprint Backlog
ID | User Story | Tasks | Estimate | Owner | Status
US001 | As a user, I want to be able to create a new account. | Task 1: Create the user registration | 5 | Rohan | In progress
|  | Task 2: Create the high level doc design | 4 | Sharayu | In progress
|  | Task 3: Create the DB design | 3 | Venkat | Not started
|  | Task 4: Create the user login | 5 | Kaushal | Not started
|  | Task 5: Create the user functionality | 5 | Arpit | Not started
US002 |  | Task 6: |  |  | In progress
|  | Task 7: |  |  | In progress
|  | Task 8: |  |  | In progress
|  | Task 9: |  |  | Not started
|  | Task 10: |  |  | Not started